## Sheet1
phase | start_date | estimated_end_date | actual_end_date | duration | deliverables | status
Project Preparation | 2025-11-01 | 2025-11-14 | 2025-11-14 | 13 | Literature Review, Experimental Design, Equipment List | Completed
Data Collection | 2025-11-15 | 2025-11-21 | 2025-11-21 | 6 | 49,984 Image Frames, Temperature Data | Completed
Data Preprocessing | 2025-11-22 | 2025-12-05 |  | 13 | Preprocessed Images, Interpolated Temperature Data | In progress
Experiment Iteration | 2025-12-01 | 2025-12-14 |  | 13 | Experiment logs, preliminary results | In progress
Data Annotation | 2025-12-06 | 2025-12-30 |  | 24 | Annotated Dataset (158 Training, 333 Validation) | Unfinished
YOLO Model Development | 2025-12-31 | 2026-01-24 |  | 24 | Trained YOLOv12s Model | Unfinished
Model Validation & Testing | 2026-01-25 | 2026-02-05 |  | 11 | Performance Report, Detection Results | Unfinished
Motion Intensity Analysis | 2026-02-06 | 2026-02-21 |  | 15 | Motion Analysis Results, Prediction Model | Unfinished
Result Analysis & Visualization | 2026-02-22 | 2026-03-03 |  | 9 | Analysis Report, Visualization Charts | Unfinished
Paper Writing | 2026-03-04 | 2026-03-23 |  | 19 | Academic Paper | Unfinished