## Sheet1
phase | start_date | end_date | duration | deliverables | resources | status
Project Preparation | 2025-11-01 | 2025-11-14 | 14 | Literature Review, Experimental Design, Equipment List | 1 Researcher | Planned
Data Collection | 2025-11-15 | 2025-11-21 | 7 | 49,984 Image Frames, Temperature Data | 1 Researcher | Planned
Data Preprocessing | 2025-11-22 | 2025-12-05 | 14 | Preprocessed Images, Interpolated Temperature Data | 1 Researcher | Planned
Data Annotation | 2025-12-06 | 2025-12-30 | 25 | Annotated Dataset (158 Training, 333 Validation) | 2 Researchers | Planned
YOLO Model Development | 2025-12-31 | 2026-01-24 | 25 | Trained YOLOv12s Model | 1 Researcher, GPU Server | Planned
Model Validation & Testing | 2026-01-25 | 2026-02-05 | 12 | Performance Report, Detection Results | 1 Researcher | Planned
Motion Intensity Analysis | 2026-02-06 | 2026-02-21 | 16 | Motion Analysis Results, Prediction Model | 1 Researcher | Planned
Result Analysis & Visualization | 2026-02-22 | 2026-03-03 | 10 | Analysis Report, Visualization Charts | 1 Researcher | Planned
Paper Writing | 2026-03-04 | 2026-03-23 | 20 | Academic Paper | 1 Researcher | Planned